Senior Design - Milestone, Timeline and Effort Matrix

Team Members:

Saugat Ghimire

Aayush Pokhrel

Sabal Dahal

## Milestones List

- Milestone 1 – Research Completed
 Completion of literature review and selection of baseline deep learning model.

- Milestone 2 – ML Model Ready
 Preprocessing, training, and refinement of deep learning model finished.

- Milestone 3 – Backend Implemented
 Database schema, APIs, and authentication system operational.

- Milestone 4 – Frontend Implemented
 UI design, monitoring features, and alert system completed.

- Milestone 5 – System Integration & Testing
 ML, backend, and frontend integrated, with functional testing completed.

- Milestone 6 – Final Documentation & Demo
 Submission of documentation, report, and final presentation.

Timeline Table

| Task | Task Description | Responsible | Start Date | End Date | Milestone |
| --- | --- | --- | --- | --- | --- |
| 1 | Research DL models | Sabal | Oct 7, 2025 | Oct 31, 2025 | M1 |
| 2 | Collect / preprocess images | Sabal | Oct 7, 2025 | Nov 15, 2025 | M2 |
| 3 | Design ML training pipeline | Sabal | Oct 20, 2025 | Nov 10, 2025 | M2 |
| 4 | Train / evaluate baseline model | Sabal | Nov 11, 2025 | Dec 1, 2025 | M2 |
| 5 | Refine model architecture | Sabal | Dec 2, 2025 | Dec 15, 2025 | M2 |
| 6 | Specify database schema | Aayush | Nov 10, 2025 | Nov 20, 2025 | M3 |
| 7 | Develop backend API | Aayush | Nov 21, 2025 | Dec 15, 2025 | M3 |
| 8 | Integrate ML with backend | Aayush | Jan 5, 2026 | Jan 20, 2026 | M3 |
| 9 | Implement authentication | Aayush | Jan 5, 2026 | Jan 20, 2026 | M3 |
| 10 | Test backend modules | Aayush | Jan 21, 2026 | Jan 31, 2026 | M3 |
| 11 | Design dashboard UI | Saugat | Nov 21, 2025 | Dec 15, 2025 | M4 |
| 12 | Develop monitoring features | Saugat | Jan 5, 2026 | Jan 25, 2026 | M4 |
| 13 | Implement alerts / notifications | Saugat | Jan 26, 2026 | Feb 10, 2026 | M4 |
| 14 | Validate UI/UX | Saugat | Feb 11, 2026 | Feb 20, 2026 | M4 |
| 15 | Document frontend code | Saugat | Feb 21, 2026 | Feb 28, 2026 | M4 |
| 16 | Integrate subsystems | Team | Mar 1, 2026 | Mar 10, 2026 | M5 |
| 17 | Conduct system-wide testing | Team | Mar 11, 2026 | Mar 20, 2026 | M5 |
| 18 | Evaluate performance / refine | Team | Mar 11, 2026 | Mar 20, 2026 | M5 |
| 19 | Prepare project documentation | Team | Mar 21, 2026 | Mar 28, 2026 | M6 |
| 20 | Final demo | Team | Apr 1, 2026 | Apr 5, 2026 | M6 |

| Task # | Task Description | Sabal (%) | Aayush (%) | Saugat (%) |
| --- | --- | --- | --- | --- |
| 1 | Research DL models | 70.0 | 15.0 | 15.0 |
| 2 | Collect / preprocess images | 70.0 | 15.0 | 15.0 |
| 3 | Design ML training pipeline | 70.0 | 15.0 | 15.0 |
| 4 | Train / evaluate baseline model | 70.0 | 15.0 | 15.0 |
| 5 | Refine model architecture | 70.0 | 15.0 | 15.0 |
| 6 | Specify database schema | 15.0 | 70.0 | 15.0 |
| 7 | Develop backend API | 15.0 | 70.0 | 15.0 |
| 8 | Integrate ML with backend | 15.0 | 70.0 | 15.0 |
| 9 | Implement authentication | 15.0 | 70.0 | 15.0 |
| 10 | Test backend modules | 15.0 | 70.0 | 15.0 |
| 11 | Design dashboard UI | 15.0 | 15.0 | 70.0 |
| 12 | Develop monitoring features | 15.0 | 15.0 | 70.0 |
| 13 | Implement alerts / notifications | 15.0 | 15.0 | 70.0 |
| 14 | Validate UI/UX | 15.0 | 15.0 | 70.0 |
| 15 | Document frontend code | 15.0 | 15.0 | 70.0 |
| 16 | Integrate subsystems | 33.3 | 33.3 | 33.3 |
| 17 | Conduct system-wide testing | 33.3 | 33.3 | 33.3 |
| 18 | Evaluate performance / refine | 33.3 | 33.3 | 33.3 |
| 19 | Prepare project documentation | 33.3 | 33.3 | 33.3 |
| 20 | Present final demo | 33.3 | 33.3 | 33.3 |